PLAN OF ACTION AND MILESTONES (POA&M) MASTER TRACKER

CloudVault Federal Health Exchange (FHX)

Document ID: CV-FHX-POAM-001 ¦ Version: 2.1 ¦ Classification: UNCLASSIFIED // FOR OFFICIAL USE ONLY (FOUO)

| Field | Detail |
| --- | --- |
| Prepared By: | Enechi P.C. Njeze — Information System Security Officer (ISSO) and Information System Security Manager (ISSM) |
| Certifications: | CGRC, CISA, CISM, PMP, PMI-RMP, CompTIA Security+ SY0-701, CHP, CSCS, CISSP (in progress) |
| Reviewed By: | Henry Kline, Deputy Director and Authorizing Official (AO) |
| SAISO: | Marcus T. Brennan, Senior Agency Information Security Officer |
| Organization: | Federal Health Data Office (FHDO), CloudVault FHX Program |
| Reporting Period: | March 1, 2026 through March 31, 2026 |
| Next Submission: | April 30, 2026 |
| Document Status: | ACTIVE |

Related Documents

System Security Plan: ../docs/system-security-plan.md

FIPS 199 Security Categorization: ../assessments/fips199-security-categorization.md

Security Assessment Plan: ../assessments/security-assessment-plan.md

Continuous Monitoring Strategy: ../conmon/README.md

Authorization Package: ../authorization/README.md

# 1. Purpose and Scope

## 1.1 Purpose

This Plan of Action and Milestones (POA&M) Master Tracker documents all known security weaknesses, deficiencies, and control gaps identified in the CloudVault Federal Health Exchange (FHX) through security assessments, continuous monitoring activities, vulnerability scanning, penetration testing, and self-identified internal reviews. It establishes the corrective action milestones, responsible parties, and target completion dates required to address each weakness.

The POA&M is a living document and a federally mandated artifact under FISMA (44 U.S.C. § 3554), OMB Memorandum M-02-01, and FedRAMP Continuous Monitoring requirements. It is submitted monthly to the Authorizing Official and updated whenever new weaknesses are identified or existing items are closed, delayed, or re-assessed.

## 1.2 Scope

This POA&M covers all security weaknesses identified within the CloudVault FHX authorization boundary as defined in the System Security Plan (SSP) Section 3. It does not cover weaknesses in inherited AWS GovCloud controls (tracked in the AWS CSP's POA&M) or interconnected agency systems operating under separate ATOs.

## 1.3 POA&M ID Convention

Each POA&M item is assigned a unique identifier using the format: CV-FHX-POAM-[YEAR]-[SEQUENCE]

Example: CV-FHX-POAM-2026-001 is the first weakness formally opened in calendar year 2026.

# 2. POA&M Summary Dashboard

## 2.1 Current Status Overview — March 2026

| Metric | Count |
| --- | --- |
| Total Open POA&M Items | 14 |
| Critical (Very High Risk) Items Open | 1 |
| High Risk Items Open | 3 |
| Moderate Risk Items Open | 6 |
| Low Risk Items Open | 4 |
| Items Closed This Reporting Period | 3 |
| Items Past Due / Overdue | 1 |
| Items with Approved Extensions | 2 |
| Items with Active Compensating Controls | 4 |
| New Items Opened This Period | 2 |

## 2.2 Risk Posture Trend (October 2025 — March 2026)

| Month | Critical | High | Moderate | Low | Total Open | Trend |
| --- | --- | --- | --- | --- | --- | --- |
| Oct 2025 (Initial ATO) | 2 | 5 | 9 | 7 | 23 | Baseline |
| Nov 2025 | 2 | 5 | 8 | 6 | 21 | ▼ -2 |
| Dec 2025 | 1 | 4 | 8 | 5 | 18 | ▼ -3 |
| Jan 2026 | 1 | 4 | 7 | 5 | 17 | ▼ -1 |
| Feb 2026 | 1 | 3 | 7 | 4 | 15 | ▼ -2 |
| Mar 2026 (Current) | 1 | 3 | 6 | 4 | 14 | ▼ -1 ✓ |

Trend Assessment: The overall risk posture is IMPROVING. Total open items decreased from 23 at initial ATO to 14 in the current period — a 39% reduction over five months. The one remaining Critical item (CV-FHX-POAM-2025-001) is actively being remediated with AO-approved extension through June 30, 2026.

## 2.3 Control Family Distribution of Open Items

| Family | Description | Open Items | Highest Severity |
| --- | --- | --- | --- |
| AC | Access Control | 3 | High |
| AU | Audit and Accountability | 2 | Moderate |
| CM | Configuration Management | 3 | Critical |
| IA | Identification and Authentication | 2 | High |
| SC | System and Communications Protection | 2 | Moderate |
| SI | System and Information Integrity | 1 | High |
| CP | Contingency Planning | 1 | Low |

# 3. Risk Rating and Severity Definitions

| Severity | CVSS Range | NIST Risk Level | POA&M Resolution Requirement | Monthly Reporting |
| --- | --- | --- | --- | --- |
| Critical | 9.0 – 10.0 | Very High | Within 30 days of ATO — AO escalation required | Required — AO escalation |
| High | 7.0 – 8.9 | High | Within 90 days of ATO | Required |
| Moderate | 4.0 – 6.9 | Moderate | Within 180 days of ATO | Required |
| Low | 0.1 – 3.9 | Low | Within 365 days of ATO | Required |
| Informational | N/A | Info | No POA&M required | Optional |

# 4. Open POA&M Items

## 4.1 Critical Items

| POA&M ID: CV-FHX-POAM-2025-001 |  |
| --- | --- |
| Control(s) | CM-6 (Configuration Settings), CM-7 (Least Functionality) |
| Weakness Title | Unrestricted Outbound Network Egress on Production Application Tier |
| Discovery Source | 3PAO Penetration Test (October 2025) |
| Discovery Date | October 14, 2025 |
| Severity | Critical (Very High) |
| CVSS Score | 9.1 — AV:N/AC:L/PR:L/UI:N/S:C/C:H/I:H/A:H |
| Status | In Remediation — AO-Approved Extension through June 30, 2026 |
| Responsible Party | Trevor L. Abrams, Cloud Operations Lead |
| ISSO Oversight | Enechi P.C. Njeze |
| Original Target Date | November 13, 2025 |
| Revised Target Date | June 30, 2026 |
| Extension Approved | Yes — AO approved December 2, 2025 |
| Compensating Control | CV-FHX-CC-001 (Enhanced CloudWatch Egress Monitoring — see Section 8) |
| Weakness Description & Corrective Action Plan |  |
| WEAKNESS: Production application tier EC2 instances permit unrestricted outbound network egress (0.0.0.0/0 on all outbound ports) via overly permissive VPC security group rules. A penetration test confirmed successful simulated PHI/FTI exfiltration through this path during authorized testing on October 14, 2025. THREAT SCENARIO: An adversary achieving code execution on any application tier instance could exfiltrate all PHI and FTI (890,000+ patient records in scope) to an attacker-controlled external server with no network-layer blocking in place. CORRECTIVE ACTION PLAN: 1. Implement egress filtering rules in all production VPC security groups restricting outbound traffic to approved destinations only. 2. Deploy AWS Network Firewall with domain-based egress filtering policies. 3. Implement VPC Flow Logs-based egress anomaly detection in Amazon GuardDuty. 4. Conduct regression penetration test to validate full remediation. 5. Update SSP network architecture description to reflect new egress controls. |  |
| Milestones |  |
| Milestone 1 — COMPLETED | Security group egress rule restriction to approved destinations only Completed: January 15, 2026 |
| Milestone 2 — COMPLETED | AWS Network Firewall policy development and internal review Completed: February 28, 2026 |
| Milestone 3 — IN PROGRESS | Network Firewall staging deployment to non-production environment Target: April 30, 2026 |
| Milestone 4 — PENDING | Network Firewall production deployment across all VPCs Target: June 15, 2026 |
| Milestone 5 — PENDING | Regression penetration test validation and POA&M closure Target: June 30, 2026 |

## 4.2 High Risk Items

| POA&M ID: CV-FHX-POAM-2025-003 |  |
| --- | --- |
| Control(s) | AC-2 (Account Management), AC-3 (Access Enforcement) |
| Weakness Title | Stale Privileged Accounts Not Removed After Personnel Departure |
| Discovery Source | 3PAO Assessment — Interview and Examination (October 2025) |
| Discovery Date | October 16, 2025 |
| Severity | High |
| CVSS Score | 8.1 — AV:N/AC:L/PR:L/UI:N/S:U/C:H/I:H/A:N |
| Status | In Remediation — Extension Approved |
| Responsible Party | Trevor L. Abrams, Cloud Operations Lead |
| ISSO Oversight | Enechi P.C. Njeze |
| Original Target Date | January 14, 2026 |
| Revised Target Date | March 31, 2026 |
| Extension Approved | Yes |
| Compensating Control | N/A |
| Weakness Description & Corrective Action Plan |  |
| WEAKNESS: Seven privileged IAM accounts belonging to personnel who separated from FHDO between January–September 2025 were found active at time of assessment. Two accounts retained active access keys with no expiration date, violating AC-2(j) (24-hour removal requirement) and AC-2(3) (35-day inactivity disable under FedRAMP High baseline). CORRECTIVE ACTION PLAN: 1. Immediately disable all 7 stale accounts and revoke active access keys. [Completed Oct 17, 2025] 2. Implement automated IAM account lifecycle management integrated with FHDO HR offboarding process. 3. Deploy AWS IAM Access Analyzer to continuously detect unused credentials and orphaned accounts. 4. Update and enforce the AC-2 account management procedure with mandatory 24-hour offboarding notification to Cloud Operations. 5. Conduct quarterly privileged account access reviews per AC-2(j). |  |
| Milestones |  |
| Milestone 1 — COMPLETED | Stale account disablement and active access key revocation Completed: October 17, 2025 |
| Milestone 2 — COMPLETED | AWS IAM Access Analyzer deployment for continuous orphaned account detection Completed: December 10, 2025 |
| Milestone 3 — COMPLETED | HR-IAM integration automation for offboarding workflow Completed: February 14, 2026 |
| Milestone 4 — IN PROGRESS | Updated AC-2 account management procedure — pending final approval Target: March 31, 2026 |
| Milestone 5 — PENDING | First quarterly privileged access review per AC-2(j) Target: April 30, 2026 |

| POA&M ID: CV-FHX-POAM-2025-007 |  |
| --- | --- |
| Control(s) | IA-5 (Authenticator Management), IA-5(1) (Password-Based Authentication) |
| Weakness Title | Non-Compliant Password Policy on Administrative Console |
| Discovery Source | 3PAO Technical Assessment (October 2025) |
| Discovery Date | October 20, 2025 |
| Severity | High |
| CVSS Score | 7.5 — AV:N/AC:L/PR:N/UI:N/S:U/C:H/I:N/A:N |
| Status | In Remediation — Extension Approved (MFA implementation requires vendor coordination) |
| Responsible Party | Trevor L. Abrams, Cloud Operations Lead |
| ISSO Oversight | Enechi P.C. Njeze |
| Original Target Date | January 18, 2026 |
| Revised Target Date | April 30, 2026 |
| Extension Approved | Yes |
| Compensating Control | CV-FHX-CC-002 (VPN + CloudTrail/GuardDuty privileged session monitoring) |
| Weakness Description & Corrective Action Plan |  |
| WEAKNESS: The administrative console enforced an 8-character minimum password policy with no complexity requirements and no prohibition on previously used passwords. FedRAMP High baseline IA-5(1) requires: 15-character minimum, 24-password history restriction, and mandatory password change upon initial login. Non-compliant policy was applied to 23 administrative accounts. CORRECTIVE ACTION PLAN: 1. Update administrative console password policy to 15-character minimum with complexity enforcement. 2. Implement 24-password history restriction. 3. Force password resets for all 23 affected administrative accounts. 4. Evaluate and implement FIDO2 phishing-resistant MFA for all privileged accounts per OMB M-22-09. 5. Document updated IA-5 authenticator management procedures. |  |
| Milestones |  |
| Milestone 1 — COMPLETED | Password policy update to 15-char minimum and forced resets for 23 admin accounts Completed: January 30, 2026 |
| Milestone 2 — COMPLETED | FIDO2 MFA vendor selection and procurement initiation Completed: March 1, 2026 |
| Milestone 3 — IN PROGRESS | FIDO2 MFA pilot deployment for 5 administrative accounts Target: April 15, 2026 |
| Milestone 4 — PENDING | Full FIDO2 MFA rollout to all 23 admin accounts and documentation update Target: April 30, 2026 |
| Milestone 5 — N/A | N/A |

| POA&M ID: CV-FHX-POAM-2026-001 |  |
| --- | --- |
| Control(s) | SI-2 (Flaw Remediation), CM-8 (System Component Inventory) |
| Weakness Title | Critical CVE Unpatched on Three Application Tier Instances |
| Discovery Source | Monthly Vulnerability Scan (February 2026) |
| Discovery Date | February 5, 2026 |
| Severity | High |
| CVSS Score | 8.8 — AV:N/AC:L/PR:L/UI:N/S:U/C:H/I:H/A:H |
| Status | Open — New This Reporting Period (Actively Being Remediated) |
| Responsible Party | Trevor L. Abrams, Cloud Operations Lead |
| ISSO Oversight | Enechi P.C. Njeze |
| Original Target Date | March 14, 2026 |
| Revised Target Date | April 14, 2026 |
| Extension Approved | No |
| Compensating Control | CV-FHX-CC-003 (Affected instances placed in restricted security group — no inbound internet access) |
| Weakness Description & Corrective Action Plan |  |
| WEAKNESS: CVE-2026-11842 (CVSS 8.8 — Remote Code Execution via Java deserialization vulnerability) identified as unpatched on three EC2 application tier instances (i-0a1b2c3d4e, i-0f5a6b7c8d, i-0e9f1a2b3c). Vendor patch was released January 28, 2026. The 30-day patching SLA defined in the CloudVault FHX SI-2 implementation requires remediation by February 28, 2026 for High severity vulnerabilities. The three instances were missed during the February patch cycle due to a gap in the patch management automation workflow. CORRECTIVE ACTION PLAN: 1. Apply CVE-2026-11842 patch to all three affected instances within 5 business days of POA&M opening. 2. Verify patch application through authenticated re-scan of all three instances. 3. Identify and remediate the patch management automation gap that caused the missed instances. 4. Conduct unscheduled full-environment patch compliance scan to identify any other missed instances. 5. Update the SI-2 patch management procedure to include automated inventory reconciliation before each patch cycle closes. |  |
| Milestones |  |
| Milestone 1 — IN PROGRESS | Emergency patch application to all three affected EC2 instances Target: March 7, 2026 |
| Milestone 2 — PENDING | Authenticated verification re-scan of all three instances Target: March 10, 2026 |
| Milestone 3 — PENDING | Patch automation gap analysis and technical remediation Target: March 28, 2026 |
| Milestone 4 — PENDING | Full-environment unscheduled patch compliance scan Target: March 31, 2026 |
| Milestone 5 — PENDING | Updated SI-2 patch management procedure approval Target: April 14, 2026 |

## 4.3 Moderate Risk Items — Summary View

| POA&M ID | Control(s) | Weakness Title | Target Date | Status |
| --- | --- | --- | --- | --- |
| CV-FHX-POAM-2025-004 | AU-9, AU-11 | Audit log retention not meeting 12-month online requirement | Apr 30, 2026 | In Remediation |
| CV-FHX-POAM-2025-008 | SC-8, SC-8(1) | TLS 1.0 and 1.1 not disabled on two legacy API endpoints | Apr 15, 2026 | In Remediation |
| CV-FHX-POAM-2025-010 | CM-2, CM-3 | Configuration baseline documentation not updated after last infrastructure change | Mar 31, 2026 | OVERDUE — AO Notified Mar 3, 2026 |
| CV-FHX-POAM-2025-014 | AC-17, AC-17(1) | Remote access session timeout set to 4 hours (FedRAMP High requires 30 minutes) | Apr 30, 2026 | In Remediation |
| CV-FHX-POAM-2026-002 | AU-2, AU-12 | Three event categories missing from audit logging configuration | May 15, 2026 | Open — New This Period |
| CV-FHX-POAM-2025-019 | AC-6, AC-6(5) | Four service accounts have excessive privilege beyond least-privilege baseline | May 31, 2026 | In Remediation |

## 4.4 Low Risk Items — Summary View

| POA&M ID | Control | Weakness Title | Target Date | Status |
| --- | --- | --- | --- | --- |
| CV-FHX-POAM-2025-011 | PL-4 | Rules of behavior acknowledgment not documented for two new contractors | Apr 30, 2026 | In Remediation |
| CV-FHX-POAM-2025-015 | CP-4 | Contingency plan test results not documented in required format | May 31, 2026 | In Remediation |
| CV-FHX-POAM-2025-018 | SA-22 | One unsupported third-party library identified (vendor EOL January 2026) | Jun 30, 2026 | In Remediation |
| CV-FHX-POAM-2025-022 | AT-2 | Annual security awareness training overdue for three personnel | Apr 15, 2026 | In Remediation |

# 5. Closed POA&M Items — March 2026 Reporting Period

| POA&M ID | Control | Weakness Title | Severity | Closure Date | Closure Evidence |
| --- | --- | --- | --- | --- | --- |
| CV-FHX-POAM-2025-002 | AC-11 | Session lock not enforcing after 15-minute inactivity | High | Mar 5, 2026 | Session policy screenshot; 3PAO verification email dated March 7, 2026 |
| CV-FHX-POAM-2025-005 | IA-2(1) | MFA not enforced for privileged access to one subsystem | High | Mar 12, 2026 | AWS IAM MFA policy screenshot; authenticated test confirmation from DevOps Lead |
| CV-FHX-POAM-2025-016 | CM-10 | Software license tracking spreadsheet not maintained | Low | Mar 20, 2026 | Updated license inventory workbook v2.0; approved by Cloud Operations Lead |

March 2026 Closure Summary: 3 items closed (2 High, 1 Low). The closure of CV-FHX-POAM-2025-005 (MFA for privileged access) is a significant security improvement that eliminates a known credential-based attack path on the administrative subsystem. All closure evidence reviewed and accepted by the ISSO.

# 6. Delayed and At-Risk Items

## 6.1 Overdue Items

| POA&M ID | Original Due Date | Overdue By | Severity | AO Notified | Reason for Delay |
| --- | --- | --- | --- | --- | --- |
| CV-FHX-POAM-2025-010 | February 28, 2026 | 1 Month | Moderate | March 3, 2026 | Configuration baseline update blocked pending Architecture Review Board (ARB) approval. ARB meeting scheduled March 25, 2026. |

ISSO Action: AO was notified March 3, 2026 per FedRAMP continuous monitoring requirements. ARB meeting scheduled March 25, 2026. If approval is obtained, baseline documentation update and POA&M closure expected by March 31, 2026.

## 6.2 At-Risk Items — On Extension or Approaching Due Date

| POA&M ID | Revised Due Date | Risk to Timeline | Mitigation Strategy |
| --- | --- | --- | --- |
| CV-FHX-POAM-2025-001 | June 30, 2026 | Medium — second extension possible if AWS Network Firewall production deployment encounters unexpected issues | Daily standup tracking between ISSO and Cloud Operations Lead; AO escalation path pre-defined |
| CV-FHX-POAM-2025-007 | April 30, 2026 | Low — FIDO2 vendor has confirmed hardware delivery schedule for all 23 admin accounts | Weekly milestone check-in scheduled with vendor and ISSO |

# 7. POA&M Governance and Update Procedures

## 7.1 Update Frequency and Submission Schedule

| Activity | Frequency | Responsible Party |
| --- | --- | --- |
| POA&M data entry and milestone updates | Weekly | ISSO — Enechi P.C. Njeze |
| Vulnerability scan integration and new item creation | Monthly (within 5 business days of scan completion) | ISSO and Cloud Operations Lead |
| Full POA&M review and AO submission | Monthly (by last business day of each month) | ISSO |
| Quarterly POA&M deep review with AO | Quarterly | ISSO, AO, SAISO |
| Annual POA&M reconciliation with SAR | Annually | ISSO, 3PAO |

## 7.2 New Item Creation Criteria

A new POA&M item is created when any of the following conditions are met:

- A security control is assessed as Other Than Satisfied (OTS) during an assessment or monitoring activity

- A vulnerability scan identifies a finding with CVSS score 4.0 or above that cannot be remediated within the standard patching SLA

- A penetration test identifies an exploitable weakness

- A security incident investigation reveals a previously unknown control gap

- The ISSO or system owner identifies a control deficiency through self-assessment or internal review

- A FedRAMP PMO review raises a finding against the authorization package

## 7.3 POA&M Closure Criteria

A POA&M item may be closed only when ALL of the following conditions are satisfied:

- All corrective action milestones have been completed

- The ISSO has reviewed and accepted the closure evidence

- The remediated control has been verified through testing, examination, or interview (as appropriate to the control type)

- The SSP has been updated to reflect the corrected control implementation statement if the implementation changed

- The closure is documented in this tracker with the closure date and evidence reference

- For Critical or High items, the 3PAO or ISSO has conducted independent verification of the remediation

# 8. Compensating Controls Register

| CC ID | Associated POA&M | Compensating Control Description | Owner | Effective / Review Date |
| --- | --- | --- | --- | --- |
| CV-FHX-CC-001 | CV-FHX-POAM-2025-001 | Enhanced Amazon CloudWatch egress anomaly detection with 15-minute alert threshold and automated Security Hub notification to ISSO. SOC reviews all egress anomaly alerts within 1 hour. | Trevor L. Abrams | Effective: Oct 20, 2025 Review: Jun 30, 2026 |
| CV-FHX-CC-002 | CV-FHX-POAM-2025-007 | Privileged admin sessions require VPN with certificate-based authentication and are monitored in real time via AWS CloudTrail and GuardDuty. All privileged actions reviewed in weekly access log audits by ISSO. | Enechi P.C. Njeze | Effective: Oct 22, 2025 Review: Apr 30, 2026 |
| CV-FHX-CC-003 | CV-FHX-POAM-2026-001 | Three affected EC2 instances placed in a restricted security group with no inbound internet access pending patch application. Application traffic routed through unaffected instances during the remediation window. | Trevor L. Abrams | Effective: Feb 6, 2026 Review: Mar 14, 2026 |
| CV-FHX-CC-004 | CV-FHX-POAM-2025-004 | Audit logs archived to Amazon S3 with 7-year retention (exceeds the 12-month online requirement). Archive encrypted with KMS; immutable object lock enabled. Online 12-month index is being rebuilt. | Trevor L. Abrams | Effective: Nov 1, 2025 Review: Apr 30, 2026 |

# 9. Vendor and Third-Party Dependency Tracker

| POA&M ID | Dependency Type | Vendor / Party | Expected Resolution | Risk to Timeline |
| --- | --- | --- | --- | --- |
| CV-FHX-POAM-2025-001 | AWS Service | Amazon Web Services — AWS Network Firewall deployment in AWS GovCloud environment | April 30, 2026 | Medium — escalation path to AO defined; daily standup in progress |
| CV-FHX-POAM-2025-007 | Vendor Product | FIDO2 MFA Vendor (TBD) — hardware key procurement and enrollment for 23 admin accounts | April 15, 2026 | Low — vendor confirmed delivery schedule |
| CV-FHX-POAM-2025-018 | Software Vendor | Third-Party Java Library Maintainer — EOL library replacement requires code refactoring and regression testing | June 30, 2026 | Low — internal development team managing replacement |
| CV-FHX-POAM-2026-001 | CVE Patch | Java Framework Vendor — CVE-2026-11842 patch compatibility testing across all three affected instances | March 14, 2026 | Low — patch available; compatibility testing in progress |

# 10. Approval and Certification

| ISSO and ISSM Certification |  |
| --- | --- |
| Name: | Enechi P.C. Njeze |
| Title: | Information System Security Officer (ISSO) and Information System Security Manager (ISSM) |
| Organization: | Federal Health Data Office (FHDO), CloudVault FHX Program |
| Certifications: | CGRC, CISA, CISM, PMP, PMI-RMP, CompTIA Security+ SY0-701, CHP, CSCS, CISSP (in progress) |
| I certify that the information contained in this Plan of Action and Milestones is accurate and complete to the best of my knowledge. All open weaknesses are being actively tracked and remediated in accordance with the timelines and milestones documented herein. All compensating controls listed in Section 8 are operational and have been verified by the ISSO. |  |
| Signature: _________________________________________ | Date: ______________________________ |

| Authorizing Official Review |  |
| --- | --- |
| Name: | Henry Kline |
| Title: | Deputy Director and Authorizing Official (AO) |
| Organization: | Federal Health Data Office (FHDO) |
| I have reviewed the March 2026 POA&M submission and concur with the risk posture described herein. The ongoing remediation of CV-FHX-POAM-2025-001 (Critical) continues to be monitored with heightened attention. The AO-approved extension through June 30, 2026 remains in effect subject to the milestone conditions documented in Section 4.1. |  |
| Signature: _________________________________________ | Date: ______________________________ |

| SAISO Concurrence |  |
| --- | --- |
| Name: | Marcus T. Brennan |
| Title: | Senior Agency Information Security Officer |
| Organization: | Federal Health Data Office (FHDO) |
| I have reviewed and concur with the security risk posture and the POA&M remediation status as documented in this report for the March 2026 reporting period. |  |
| Signature: _________________________________________ | Date: ______________________________ |