## Dashboard
PLAN OF ACTION AND MILESTONES (POA&M) MASTER TRACKER
CloudVault Federal Health Exchange (FHX) ¦ Document ID: CV-FHX-POAM-001 ¦ Version: 2.1 ¦ Classification: UNCLASSIFIED // FOUO
Prepared By: Enechi P.C. Njeze, ISSO/ISSM ¦ Reviewed By: Henry Kline, Deputy Director & AO ¦ Reporting Period: March 1–31, 2026 ¦ Next Due: April 30, 2026
CURRENT STATUS OVERVIEW — REPORTING PERIOD: MARCH 2026
Total Open POA&M Items |  |  |  |  | 14
Critical (Very High Risk) Open |  |  |  |  | 1
High Risk Open |  |  |  |  | 3
Moderate Risk Open |  |  |  |  | 6
Low Risk Open |  |  |  |  | 4
Closed This Reporting Period |  |  |  |  | 3
Items Past Due (Overdue) |  |  |  |  | 1
Items with Approved Extensions |  |  |  |  | 2
Items with Active Comp Controls |  |  |  |  | 4
New Items Opened This Period |  |  |  |  | 2
RISK POSTURE TREND (Oct 2025 → Mar 2026)
Month | Critical | High | Moderate | Low | Total Open | Trend
Oct 2025 (Initial ATO) | 2 | 5 | 9 | 7 | 23 | Baseline
Nov 2025 | 2 | 5 | 8 | 6 | 21 | ▼ -2
Dec 2025 | 1 | 4 | 8 | 5 | 18 | ▼ -3
Jan 2026 | 1 | 4 | 7 | 5 | 17 | ▼ -1
Feb 2026 | 1 | 3 | 7 | 4 | 15 | ▼ -2
Mar 2026 (Current) | 1 | 3 | 6 | 4 | 14 | ▼ -1 ✓
CONTROL FAMILY DISTRIBUTION OF OPEN ITEMS
Control Family | Description |  | Open Items |  | Highest Severity
AC | Access Control |  | 3 |  | High
AU | Audit and Accountability |  | 2 |  | Moderate
CM | Configuration Management |  | 3 |  | Critical
IA | Identification and Authentication |  | 2 |  | High
SC | System & Communications Protection |  | 2 |  | Moderate
SI | System and Information Integrity |  | 1 |  | High
CP | Contingency Planning |  | 1 |  | Low
STATUS: ACTIVE ¦ Trend Assessment: Overall risk posture IMPROVING — total open items reduced from 23 (Oct 2025 ATO) to 14 (Mar 2026), a 39% reduction over five months. The one remaining Critical item (CV-FHX-POAM-2025-001) is actively being remediated with AO-approved extension through June 30, 2026.

## Open POA&M Items
CV-FHX — OPEN POA&M ITEMS ¦ Reporting Period: March 1–31, 2026 ¦ Total Open: 14 ¦ ISSO: Enechi P.C. Njeze ¦ AO: Henry Kline
POA&M ID | Control(s) | Weakness Title | Discovery Source | Discovery Date | Severity | CVSS Score | Status | Responsible Party | ISSO Oversight | Original Target Date | Revised Target Date | Extension Approved | Comp Control Ref | Weakness Description / Corrective Action Summary | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5
── CRITICAL ITEMS (Very High Risk) ── Require AO Escalation ──
CV-FHX-POAM-2025-001 | CM-6, CM-7 | Unrestricted Outbound Network Egress on Production Application Tier | 3PAO Penetration Test (Oct 2025) | Oct 14, 2025 | Critical | 9.1 | In Remediation (Extension Approved) | Trevor L. Abrams Cloud Operations Lead | Enechi P.C. Njeze | Nov 13, 2025 | Jun 30, 2026 | Yes — AO Approved Dec 2, 2025 | CV-FHX-CC-001 | Production EC2 instances permit unrestricted outbound egress (0.0.0.0/0 all ports), enabling PHI/FTI exfiltration. Penetration test confirmed exploitability. CAP: (1) Restrict VPC SG egress rules; (2) Deploy AWS Network Firewall; (3) GuardDuty egress anomaly detection; (4) Regression pentest; (5) Update SSP network architecture. | ✓ SG egress rule restriction Completed: Jan 15, 2026 | ✓ Network Firewall policy dev Completed: Feb 28, 2026 | Network Firewall staging deploy Target: Apr 30, 2026 | Network Firewall prod deploy Target: Jun 15, 2026 | Regression pentest & closure Target: Jun 30, 2026
── HIGH RISK ITEMS ── 90-Day Resolution Requirement ──
CV-FHX-POAM-2025-003 | AC-2, AC-3 | Stale Privileged Accounts Not Removed After Personnel Departure | 3PAO Assessment — Interview & Examination (Oct 2025) | Oct 16, 2025 | High | 8.1 | In Remediation | Trevor L. Abrams Cloud Operations Lead | Enechi P.C. Njeze | Jan 14, 2026 | Mar 31, 2026 | Yes | N/A | 7 stale privileged IAM accounts found for separated personnel (Jan–Sep 2025); 2 had active access keys with no expiration. Violates AC-2(j) (24-hr removal) and AC-2(3) (35-day inactivity disable). CAP: (1) Disable accounts & revoke keys; (2) Automate IAM lifecycle w/ HR; (3) IAM Access Analyzer; (4) Update AC-2 procedure; (5) Quarterly privileged access review. | ✓ Stale account disablement Completed: Oct 17, 2025 | ✓ IAM Access Analyzer deploy Completed: Dec 10, 2025 | ✓ HR-IAM integration automation Completed: Feb 14, 2026 | Updated AC-2 procedure approval Target: Mar 31, 2026 | First quarterly access review Target: Apr 30, 2026
CV-FHX-POAM-2025-007 | IA-5, IA-5(1) | Non-Compliant Password Policy on Administrative Console | 3PAO Technical Assessment (Oct 2025) | Oct 20, 2025 | High | 7.5 | In Remediation | Trevor L. Abrams Cloud Operations Lead | Enechi P.C. Njeze | Jan 18, 2026 | Apr 30, 2026 | Yes | CV-FHX-CC-002 | Admin console enforced 8-char min with no complexity / history. FedRAMP High IA-5(1) requires 15-char min, 24-password history, change on initial login. Affected 23 admin accounts. CAP: (1) Update password policy; (2) Implement 24-pw history; (3) Force resets; (4) Deploy FIDO2 phishing-resistant MFA (OMB M-22-09); (5) Update IA-5 procedures. | ✓ Policy update & forced resets Completed: Jan 30, 2026 | ✓ FIDO2 MFA vendor selection Completed: Mar 1, 2026 | FIDO2 MFA pilot (5 admin accts) Target: Apr 15, 2026 | Full FIDO2 rollout & documentation Target: Apr 30, 2026 | N/A
CV-FHX-POAM-2026-001 | SI-2, CM-8 | Critical CVE Unpatched on Three Application Tier Instances | Monthly Vulnerability Scan (Feb 2026) | Feb 5, 2026 | High | 8.8 | Open — New This Period | Trevor L. Abrams Cloud Operations Lead | Enechi P.C. Njeze | Mar 14, 2026 | Apr 14, 2026 | No | CV-FHX-CC-003 | CVE-2026-11842 (CVSS 8.8 — RCE via Java deserialization) unpatched on 3 EC2 instances. Patch released Jan 28, 2026; missed during Feb patch cycle due to automation workflow gap. CAP: (1) Emergency patch to 3 instances; (2) Verification re-scan; (3) Automation gap fix; (4) Full-environment compliance scan; (5) Update SI-2 procedure. | Emergency patch to 3 instances Target: Mar 7, 2026 | Verification re-scan Target: Mar 10, 2026 | Patch automation gap fix Target: Mar 28, 2026 | Full-environment compliance scan Target: Mar 31, 2026 | Updated SI-2 procedure approval Target: Apr 14, 2026
── MODERATE RISK ITEMS ── 180-Day Resolution Requirement ──
CV-FHX-POAM-2025-004 | AU-9, AU-11 | Audit Log Retention Not Meeting 12-Month Online Requirement | 3PAO Assessment (Oct 2025) | Oct 2025 | Moderate | 5.4 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | Mar 30, 2026 | Apr 30, 2026 | No | CV-FHX-CC-004 | Audit logs not meeting 12-month online retention requirement. S3 archive with 7-year retention active as compensating control. | Online log index rebuild Target: Apr 30, 2026 | Verify 12-month online retention Target: Apr 30, 2026 | N/A | N/A | N/A
CV-FHX-POAM-2025-008 | SC-8, SC-8(1) | TLS 1.0 and 1.1 Not Disabled on Two Legacy API Endpoints | 3PAO Assessment (Oct 2025) | Oct 2025 | Moderate | 5.9 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | Mar 15, 2026 | Apr 15, 2026 | No | N/A | TLS 1.0 and 1.1 remain enabled on two legacy API endpoints. FedRAMP requires TLS 1.2 minimum. | Disable TLS 1.0/1.1 on Endpoint 1 Target: Apr 1, 2026 | Disable TLS 1.0/1.1 on Endpoint 2 Target: Apr 15, 2026 | Verify via scan Target: Apr 15, 2026 | N/A | N/A
CV-FHX-POAM-2025-010 | CM-2, CM-3 | Configuration Baseline Documentation Not Updated After Last Infrastructure Change | 3PAO Assessment (Oct 2025) | Oct 2025 | Moderate | 4.3 | OVERDUE — AO Notified Mar 3, 2026 | Trevor L. Abrams | Enechi P.C. Njeze | Feb 28, 2026 | Mar 31, 2026 | Pending ARB Approval | N/A | Config baseline documentation not updated after infrastructure change. Blocked pending Architecture Review Board (ARB) approval — meeting scheduled Mar 25, 2026. | ARB approval Target: Mar 25, 2026 | Baseline doc update Target: Mar 31, 2026 | N/A | N/A | N/A
CV-FHX-POAM-2025-014 | AC-17, AC-17(1) | Remote Access Session Timeout Set to 4 Hours (FedRAMP High Requires 30 Minutes) | 3PAO Assessment (Oct 2025) | Oct 2025 | Moderate | 4.8 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | Mar 30, 2026 | Apr 30, 2026 | No | N/A | Remote access session timeout configured at 4 hours. FedRAMP High baseline requires 30-minute session timeout per AC-17(1). | Update session timeout config Target: Apr 15, 2026 | Verify & test timeout enforcement Target: Apr 30, 2026 | Update SSP AC-17 implementation Target: Apr 30, 2026 | N/A | N/A
CV-FHX-POAM-2026-002 | AU-2, AU-12 | Three Event Categories Missing from Audit Logging Configuration | Continuous Monitoring Review (Feb 2026) | Feb 2026 | Moderate | 5.1 | Open — New This Period | Trevor L. Abrams | Enechi P.C. Njeze | May 15, 2026 | May 15, 2026 | No | N/A | Three required event categories not captured in CloudTrail/CloudWatch audit logging configuration. Identified during continuous monitoring review. | Identify missing event categories Target: Mar 31, 2026 | Update logging config Target: Apr 30, 2026 | Verify completeness via log review Target: May 15, 2026 | N/A | N/A
CV-FHX-POAM-2025-019 | AC-6, AC-6(5) | Four Service Accounts Have Excessive Privilege Beyond Least-Privilege Baseline | 3PAO Assessment (Oct 2025) | Oct 2025 | Moderate | 5.3 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | Apr 30, 2026 | May 31, 2026 | No | N/A | 4 service accounts identified with IAM permissions exceeding least-privilege baseline. Risk of privilege escalation if accounts compromised. | Document required permissions per account Target: Apr 15, 2026 | Implement revised IAM policies Target: May 15, 2026 | Verify via IAM Access Analyzer Target: May 31, 2026 | N/A | N/A
── LOW RISK ITEMS ── 365-Day Resolution Requirement ──
CV-FHX-POAM-2025-011 | PL-4 | Rules of Behavior Acknowledgment Not Documented for Two New Contractors | 3PAO Assessment (Oct 2025) | Oct 2025 | Low | 2.1 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | Mar 31, 2026 | Apr 30, 2026 | No | N/A | PL-4 Rules of Behavior acknowledgment missing for 2 new contractor accounts. Administrative gap — no active threat scenario. | Obtain signed RoB from both contractors Target: Apr 15, 2026 | File & document in access records Target: Apr 30, 2026 | N/A | N/A | N/A
CV-FHX-POAM-2025-015 | CP-4 | Contingency Plan Test Results Not Documented in Required Format | 3PAO Assessment (Oct 2025) | Oct 2025 | Low | 1.8 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | Apr 30, 2026 | May 31, 2026 | No | N/A | CP-4 contingency plan test results not documented in FedRAMP-required format. Test was conducted but documentation is non-compliant. | Reformat test results to FedRAMP template Target: Apr 30, 2026 | ISSO review & acceptance Target: May 31, 2026 | N/A | N/A | N/A
CV-FHX-POAM-2025-018 | SA-22 | One Unsupported Third-Party Library (Vendor EOL January 2026) | 3PAO Assessment (Oct 2025) | Oct 2025 | Low | 3.1 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | May 31, 2026 | Jun 30, 2026 | No | N/A | One third-party Java library reached EOL January 2026. Replacement requires application code refactoring and regression testing. | Identify replacement library Target: Apr 15, 2026 | Code refactoring Target: May 31, 2026 | Regression testing Target: Jun 15, 2026 | Deploy & verify Target: Jun 30, 2026 | N/A
CV-FHX-POAM-2025-022 | AT-2 | Annual Security Awareness Training Overdue for Three Personnel | 3PAO Assessment (Oct 2025) | Oct 2025 | Low | 1.5 | In Remediation | Trevor L. Abrams | Enechi P.C. Njeze | Mar 31, 2026 | Apr 15, 2026 | No | N/A | Annual security awareness training completion overdue for 3 personnel. Administrative tracking gap. | Notify 3 personnel & schedule training Target: Apr 1, 2026 | Confirm completion & update training log Target: Apr 15, 2026 | N/A | N/A | N/A

## Closed Items (Mar 2026)
CV-FHX — CLOSED POA&M ITEMS ¦ Reporting Period: March 2026 ¦ Items Closed This Period: 3 (2 High, 1 Low)
POA&M ID | Control(s) | Weakness Title | Severity | Original Target Date | Closure Date | Closure Evidence | Verified By
CV-FHX-POAM-2025-002 | AC-11 | Session Lock Not Enforcing After 15-Minute Inactivity | High | Jan 14, 2026 | Mar 5, 2026 | Screenshot of updated session policy; 3PAO verification email dated Mar 7, 2026 | Enechi P.C. Njeze (ISSO)
CV-FHX-POAM-2025-005 | IA-2(1) | MFA Not Enforced for Privileged Access to One Subsystem | High | Jan 14, 2026 | Mar 12, 2026 | AWS IAM MFA policy screenshot; authenticated test confirmation from DevOps Lead | Enechi P.C. Njeze (ISSO)
CV-FHX-POAM-2025-016 | CM-10 | Software License Tracking Spreadsheet Not Maintained | Low | Mar 14, 2026 | Mar 20, 2026 | Updated license inventory workbook (v2.0); approved by Cloud Operations Lead | Enechi P.C. Njeze (ISSO)
CLOSURE NOTE: Closing of CV-FHX-POAM-2025-005 (MFA for privileged access) is a significant security improvement that eliminates a known credential-based attack path on the administrative subsystem. All closure evidence reviewed and accepted by ISSO.

## Compensating Controls
CV-FHX — COMPENSATING CONTROLS REGISTER ¦ Active Compensating Controls: 4 ¦ ISSO: Enechi P.C. Njeze
CC ID | Associated POA&M ID | Compensating Control Description | Owner | Effective Date | Review / Expiry Date | Status
CV-FHX-CC-001 | CV-FHX-POAM-2025-001 | Enhanced Amazon CloudWatch egress anomaly detection with 15-minute alert threshold and automated Security Hub notification to ISSO. SOC reviews all egress anomaly alerts within 1 hour. | Trevor L. Abrams | Oct 20, 2025 | Jun 30, 2026 | ACTIVE
CV-FHX-CC-002 | CV-FHX-POAM-2025-007 | Privileged admin sessions require VPN with certificate-based authentication and are monitored in real time via AWS CloudTrail and GuardDuty. All privileged actions reviewed in weekly access log audits by ISSO. | Enechi P.C. Njeze | Oct 22, 2025 | Apr 30, 2026 | ACTIVE
CV-FHX-CC-003 | CV-FHX-POAM-2026-001 | Three affected EC2 instances placed in restricted security group with no inbound internet access pending patch application. Application traffic routed through unaffected instances. | Trevor L. Abrams | Feb 6, 2026 | Mar 14, 2026 | ACTIVE
CV-FHX-CC-004 | CV-FHX-POAM-2025-004 | Audit logs archived to S3 with 7-year retention (exceeds 12-month online requirement) and retrieved on demand. Online 12-month index being rebuilt. S3 archive encrypted with KMS and has immutable object lock enabled. | Trevor L. Abrams | Nov 1, 2025 | Apr 30, 2026 | ACTIVE

## Vendor Dependencies
CV-FHX — VENDOR AND THIRD-PARTY DEPENDENCY TRACKER ¦ ISSO: Enechi P.C. Njeze
POA&M ID | Dependency Type | Vendor / Party | Dependency Description | Expected Resolution | Risk to Timeline
CV-FHX-POAM-2025-001 | AWS Service | Amazon Web Services | AWS Network Firewall policy deployment requires AWS GovCloud service availability and staging environment testing per AWS shared responsibility boundaries. | Apr 30, 2026 | Medium — escalation path to AO defined
CV-FHX-POAM-2025-007 | Vendor Product | FIDO2 MFA Vendor (TBD) | FIDO2 hardware key procurement and enrollment process for 23 admin accounts requires vendor delivery and onboarding schedule. | Apr 15, 2026 | Low — vendor confirmed delivery schedule
CV-FHX-POAM-2025-018 | Software Vendor | Third-Party Java Library Maintainer | Vendor EOL library replacement requires application code refactoring and regression testing; no vendor support available. | Jun 30, 2026 | Low — internal dev team managing
CV-FHX-POAM-2026-001 | CVE Patch | Java Framework Vendor | CVE-2026-11842 patch requires framework upgrade and compatibility testing across all three affected instances. | Mar 14, 2026 | Low — patch available; internal testing in progress